## Sprint 2 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
2 | 1 | 0.1 | 1 | 0.5
1.5 | 6 | 2 | 4 | 6
0.5 |  | 6 | 6 | 0.25
6
1.205 | 0.82 | 1.36 | 1.2 | 1.44
19.28 | 5.74 | 11.016 | 13.2 | 18.36 | 67.596

## Sprint 3 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
4 | 6 | 0.1 | 1 | 6
| 4 | 4 | 4 | 6
|  | 6 | 6 | 4
|  | 4 | 4 | 2
1.1675 | 0.81 | 1.38 | 1.2 | 1.28
18.68 | 8.1 | 19.458 | 18 | 23.04 | 87.278

## Sprint 4 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
2 | 6 | 2 | 4 | 6
3 | 10 | 2 | 6 | 6
| 2 | 3 | 2 | 2
| 3 |  | 3 | 3
0.9836 | 0.81 | 0.84 | 1.35 | 0.9344
19.672 | 17.01 | 1.38 | 20.25 | 15.8848 | 74.1968

## Sprint 5 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
6 | 3 | 6 |  | 6
0.9541 | 0.82 | 0.84 | 1.35 | 0.8064
22.8984 | 2.46 | 1.38 | 0 | 4.8384 | 31.5768

## Sprint 6 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
5 | 5 | 8 | 3.5 | 5
0.5
0.9766 | 0.91 | 0.84 | 1.35 | 0.8064
19.532 | 4.55 | 1.38 | 5.4 | 4.032 | 34.894

## Sprint 7 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
15 | 10 | 1 |  | 5
0.9766 | 0.91 | 0.84 | 1.35 | 0.8064
58.596 | 9.1 | 1.38 | 0 | 4.032 | 73.108

## Dylan
Task | Estimate Time | Actual Time | Ratio
Assemble Arduino | 1 | 2 | 0.5
Communicate Between Sensor and Arduino | 1 | 0.25 | 4
User Story 1 | 0.25 | 0.4 | 0.625
Gantt Chart | 2 | 3 | 0.66667
Sprint 1 Shopping List | 2 | 5 | 0.4
Sprint 2 Shopping List | 2 | 3 | 0.66667
Software Cost Estimation | 2 | 3 | 0.66667
XBEE Research | 1 | 1 | 1
Sprint 2 Cost Estimation | 3 | 3 | 1
Business Rules | 0.5 | 0.5 | 1
ER Diagram | 0.5 | 0.5 | 1
Create Tables | 0.25 | 0.5 | 0.5
DCL Scripts | 0.5 | 0.5 | 1
Attach SD card Shield | 0.25 | 0.25 | 1
Class Diagram | 6 | 4 | 1.5
Logical Architecture | 4 | 3 | 1.3333
Update Gantt Chart | 0.5 | 0.5 | 1
Read TGS2620 Manual | 2 | 0.5 | 4
Read Sensor Data | 6 | 3 | 2
Update Logical Architecture | 1 | 2 | 0.5
Update Gantt Chart | 0.5 | 0.5 | 1
Communication between Arduino and PC | 6 | 3 | 2
Establish Handshake between XBEE and mobile | 5 | 5 | 1
Windows app connecting to Xbee back end | 8

## Thyanna
Task | Estimate Time | Actual Time | Ratio
Business Case p2 | 3 | 2 | 1.5
User Story 1 | 0.5 | 0.5 | 1
Requirements Doc | 5 | 8 | 0.625
BiWeekly Reports | 0.07 | 0.07 | 1
Sprint 1 Presentation | 0.5 | 1.5 | 0.33333
User Story Doc | 0.5 | 0.66 | 0.75758
Software Cost Estimation | 0.75 | 2 | 0.375
Man Month 1 | 1 | 1 | 1
Man Month 2 | 1 | 1 | 1
Agile Development 1 | 1 | 1.5 | 0.66667
Business Rules | 0.5 | 0.5 | 1
ER Diagram | 0.5 | 0.5 | 1
Create Tables | 0.25 | 0.5 | 0.5
DCL Scripts | 0.5 | 0.25 | 2
BiWeekly Reports p2 | 0.1 | 0.1 | 1
Logical Architecture | 4 | 3 | 1.3333
Class Diagram | 6 | 4 | 1.5
Test Scripts | 1 | 2 | 0.5
Process QA | 1 | 4 | 0.25
Business Case p4 | 0.1 | 2 | 0.05
Business Case p1 | 0.1 | 1 | 0.1
BiWeekly Report | 0.07
Calibrate Sensor | 6 | 2
Mobile Client UI | 8 | 4
Mobile client to DB ui | 1
Mobile Client DB connection | 5
Packet Formatter | 7

## Jeff
Task | Estimate Time | Actual Time | Ratio
User Story 1 | 0.25 | 0.25 | 1
Business Case p1 | 1 | 1 | 1
Functional Architecture | 1 | 0.4 | 2.5
Software Cost Estimation | 2 | 3 | 0.66667
Web Site Prototype Design/Implementation | 15 | 12 | 1.25
XBEE Research | 2 | 1 | 2
Man Month 1 | 1 | 1.5 | 0.66667
Man Month 2 | 1 | 1.5 | 0.66667
Man Month 3 | 1 | 1.5 | 0.66667
Agile Development 1 | 1 | 1.5 | 0.66667
Business Rules | 0.5 | 0.5 | 1
ER Diagram | 0.5 | 0.5 | 1
Create Tables | 1.25 | 1 | 1.25
DCL Scripts | 0.5 | 0.5 | 1
Website Drop Down | 3 | 10 | 0.3
Setup Web Host | 10 | 10 | 1
Program new arduino file system | 5 | 7 | 0.71429
Connect Mobile client to DB | 8

## Charlie
Task | Estimate Time | Actual Time | Ratio
User Story 1 | 0.3 | 0.25 | 1.2
Functional Architecture p1 | 1.5 | 2 | 0.75
Solar Panel Research | 0.5 | 0.66 | 0.75758
Software Cost Estimation | 0.33 | 1.66 | 0.1988
Arduino to PC Communication Research | 0.88 | 0.25 | 3.52
Business Case p3 | 4
Functional Architecture p2 | 1 | 2.5 | 0.4
Cost Estimation Next Sprint | 1 | 1 | 1
Business Rules | 0.5 | 0.5 | 1
ER Diagram | 0.5 | 0.5 | 1
Create Tables | 0.25 | 0.25 | 1
DCL Scripts | 0.5 | 0.5 | 1
Preliminary Research on Map GPS | 3
Shut down Use Case | 1.5 | 1.5
Update requirements doc | 0.5
Website Map Creation | 3

## Sprint 8 Cost Estimate
Team | Jeff | Thyanna | Charlie | Dylan
10 | 5 | 5 | 3 | 8
7
0.9766 | 0.91 | 0.84 | 1.35 | 0.8064
39.064 | 4.55 | 10.08 | 4.05 | 6.4512 | 64.1952